## Instructions
Agenda-Tasks Tab
Use the sheet to capture all tasks that each meeting member said they would accomplish for the weekly meeting. Automatic Conditional Formatting is built into the sheet to highlight:
Priority: Red=1, Orange=2, Yellow=3
Due Dates: Red=Past Due, Orange = 0 to 7 days, Yellow = 7 to 14 days
Adjusted Dates: Red=Past Due, Orange = 0 to 7 days, Yellow = 7 to 14 days
Comp Date: RED font if later than Due Date and GREEN if equal to or before
Completion: If the % Cmpl column is 100% or DEL (deleted) then the row will highlight green
Items were left on the sheet to show you the conditional formatting and examples from a project. Delete those rows to start your list. You can sort and filter for each meeting. Sort it into your preferred display for each meeting. Then you may want to filter on % Cmpl to remove any 100% or DEL items or filter on specific dates. Display the items that you want to discuss in the meeting.
Type the most recent meeting comments in column M. Before you start the meeting, Insert a new Column for M to push earlier comments to the right. If printing, you may not want the Comments, so select your Print Range appropriately.
If you want to tie your Goals to the tasks you are doing each week, input the Goal ID you create using the Goals sheet. The Task ID can make it easy for everyone to know which row or task you are referencing. Most people use the Row number and not the Task ID column.
Discussion Tab
You can put items you want to discuss at the Weekly Meeting on this sheet. The Date column allows you to identify the items by meeting date. The Select column allows you to pick specific items, even ones from previous meeting dates. Remember that a filter in one column will limit the items filtered in another column.
If you add a meeting discussion item, put the Date input, and your name/initials in the Input by column. If you know who is the Responsible person for that topic, put their name in that column. If you want the topic discussed at the next meeting put a Y in the Select column or leave it blank for the Meeting facilitator.
You can add notes in the columns to the right of the Person column. It is typically best to not print those columns.
Goals
Capture the goals you want to achieve for this year or your next 12 months. Identify your goals in four categories, as shown at the top of the sheet. If you are using the GR8 Results System, you have identified the goals, and those now can be used with the Agenda-Tasks sheet by entering the Goal ID for each task. That helps each person know that the task entered links to a goal.
If you are uncertain about creating clear goals, you can look at the Goals Example sheet. Also, always use the SMART acrostic. Specific, Measurable, Acceptable, Result-oriented, Time bound.
Slogans, Core Values, Leader Behaviors, Brand Promise
If you are working on these items, the worksheets can be used to capture your ideas and prioritize them.

## Agenda-Tasks
Hover the cursor over B1 to see Note that describes the columns
FOR EACH MEETING
1) Filter for less than 100% complete
2) For meetings, you can Hide rows 1-7 on this worksheet
3) Insert a new column between Adj Date (Col K) and most recent Notes (Col L) for next meetings notes
4) If Printing - Select columns A - L and the desired rows. Select Print Selection and Fit Columns
Task ID | Goal ID | Person | Category | SubCat | Priority | Item or Task Description | % Cmpl | Input Date | Due Date | Adj Date | Comp Date | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments | dd/mm/yy Comments
|  | HEE | DONOR |  | 1 | Identify top 3-5 donors to consider donating the full budget for 1 year | 100% | 2022-03-15 | 2022-03-25 |  | 2022-03-25
| C1 | HEE | WEBSITE | PAGES | 1 | Change Donate buttons to Pay It Forward on Home page | 100% | 2022-04-15 | 2022-04-20 |  | 2022-04-20
|  | HEE | WEBSITE | PAGES | 1 | Change Donate buttons to Pay It Forward on Product Page | 100% | 2022-04-15 | 2022-04-20 |  | 2022-04-22
|  | HEE | WEBSITE | COURSES | 1 | Create Apprentice Course & Product for Book 1 "How Did This Happen to Me?" |  | 2022-09-01 | 2022-09-30
|  | HEE | KEAP | CONTACTS | 1 | Take Old Format Video page down | 90% | 2022-08-12 |  |  |  | Removed page from menu, but it is still available
|  | HEE | KEAP | CONTACTS | 1 | Email Subscribers and Customers that they need to sign up for the new courses because the old courses page will be taken down by ___. No course progress will be carried over. If you have a special need for the old progress, email us. | DEL | 2022-08-12
|  | HEE | WEBSITE | PAGES | 1 | Add Naming PIF Recipient to TY Page | DEL | 2022-05-01
|  | HEE | WEBSITE | PAGES | 1 | If I make changes to TC Cart design does it automatically change the others? | DEL
|  | HEE | WEBSITE | FUNCTION | 1 | Add wording to courses about choosing PURCHASE if $0 | 95% | 2022-09-12 |  |  |  | Currently not needed since "One-time" is the default. Joshua is looking at how to choose the default on PIF first
|  | HEE | WEBSITE |  | 2 | Find way to auto post or send post from WP to FB, T, etc. | 100% | 2022-03-15 | 2022-03-25 |  | 2022-03-25
|  | HEE | BUDGET |  | 2 | Identify the specific costs related to GR8R | 100% | 2022-03-15 | 2022-03-31 |  | 2022-03-31
|  | HEE | WEBSITE | PAGES | 2 | Change Log in/Out to only display on TA pages | 100% | 2022-06-11 | 2022-06-30 |  | 2022-06-16 | Decided to not do that, but did create an Apprentice menu and Main Menu
|  | HEE | WEBSITE | PAGES | 2 | Copy Kolbe, FIROB, and TKI pages to GR8R. Change wording for relationships | 100% | 2022-07-13 | 2022-07-18 |  | 2022-07-22
|  | HEE | KEAP | CONTACTS | 2 | Email current KEAP list. Tell them about the new strategy and ask them to consider PIF. Send them a monthly 2022 report? |  | 2022-05-01
|  | HEE | DONOR |  | 3 | Create list of others that might be willing to help with smaller monthly $ | 10% | 2022-03-15 | 2022-03-25
|  | HEE | ADMIN |  | 3 | Update Thrive Comments styling for pages and posts on site | 100% | 2022-03-15 | 2022-03-31 |  | 2022-04-15
|  | HEE | FREEBIE |  | 3 | Create list of items in Forms folder available to send to donors | 100% | 2022-03-31 | 2022-04-19 |  | 2022-04-19
|  | HEE | WEBSITE | FUNCTION | 3 | Write project details and find a contractor to build out Woo like TC process | DEL | 2022-05-15 | 2022-06-15 |  |  | Post on UpWork, Fiverr, GigHub, etc.
|  | HEE | WEBSITE | PAGES | 3 | Update the FAQ page | 85% | 2022-07-10 | 2022-07-30 |  |  | This was fixed earlier by disabling Cart Fragments under Nexcess, but that does not solve it now
|  | HEE | ADMIN |  | 3 | Grammarly the GR8R book |  | 2022-06-10 |  |  |  | Delegate to Latisha?
|  | HEE | FUNNEL | EMAILS | 3 | Send DM no response sequence emails from current GR8L funnels | DEL | 2022-05-01
|  | HEE | KEAP | EMAILS | 3 | Change Footer company address back to 1 line | DEL | 2022-09-01
|  | HEE | WEBSITE | FUNCTION | 3 | Create Frontend Filters (Thrive Element) for Posts, TV Shows, Podcasts, Courses |  | 2022-09-23 |  |  |  | See this post - https://thrivethemes.com/updates-september-2022/
|  | HEE | WEBSITE | MENU | 3 | Determine the best location for JOIN (Free Resources, use as the Landing Page) |  | 2022-05-15 |  |  |  | Separate menu item and button
|  | HEE | WEBSITE |  | 3 | Determine how to auto capture the number of videos a person has completed? Use a timer if too complex. Use this to capture testimonials and comments | DEL | 2022-05-01 |  |  |  | Using a timer in KEAP will be easy based on when someone gets tagged as a Subscriber. Maybe Automator can do it. Another option is a POPUP or PIF button on specific videos. Joshua created Thrive Automator that can do it.
|  | HEE | WEBSITE | FUNCTION | 3 | Sign In button on EVERY Course/Product - HIDE button if Logged In | DEL | 2022-05-01 |  |  |  | Necessary? When clicking Start or Continue, it takes them to the Log In / Sign In page.
|  | HEE | WEBSITE | FUNCTION | 3 | Populate PIF Person name and email on form with PIF Recipient for PIF Person email to PIF Recipient. Display a picture of the email on the PIF Recipient page. Provide simple and clear information about what will happen when they click SubmitExplain that when they click Submit, the email will be sent to the PIF Recipient. | DEL | 2022-05-01 |  |  |  | This is downgraded to a second level item. Work on it after everything else is working. See PJT task about Refer a Friend
|  | HEE | WEBSITE |  | 3 | Determine if pictures for current Shop need to be changed to new colors | DEL | 2022-05-01 |  |  |  | Not doing this. Use pictures without info at the bottom in Apprentice? No changes needed if we do that
|  | HEE | WEBSITE | PAGES | 3 | Add the complete narrative from the GR8R book for each Course as a Resource |  | 2022-06-10 |  |  |  | Easy add as a resource on the last video. Can it be hidden until video is watched?.
|  | HEE | DONOR |  |  | Send list of different level names from Thrive to Tina | 100% | 2022-03-15 | 2022-03-21 |  | 2022-03-25
|  | HEE | SOCIAL |  |  | Make Tina an Editor on FB | 100% |  | 2022-03-21 |  | 2022-03-21
|  | HEE | SOCIAL |  |  | Research how to use Yoast to post FB and Twitter | 100% | 2022-03-15 | 2022-03-22 |  | 2022-03-22
|  | HEE | MONEY |  |  | Identify who can write grants (Tina, Jordan Rundgren) | 100% | 2022-03-15 | 2022-03-31 |  | 2022-04-15
|  | HEE | ADMIN |  |  | Share GR8RGraphics Folder with Tina | 100% | 2022-05-15 | 2022-05-18 |  | 2022-05-18
|  | HEE | ADMIN |  |  | Specify what PIF pays for to use in Payment cart messages and ? | 95% | 2022-05-15 | 2022-05-20 |  |  | See Donor tab
|  | HEE | ADMIN |  |  | Create new header with new logo for NUDGE | 100% | 2022-05-15 | 2022-05-20 |  | 2022-05-20
|  | HEE | ADMIN |  |  | Change NUDGE and Devotions - Header, verse to H2 and add spacing on top, Font to Tahoma (H1-24, H2-22, Normal-16), PIF picture for next week - how much time required | DEL | 2022-05-15 | 2022-05-20 |  | 2022-05-20 | Doing this each week but simplified the process by using a picture for all the bottom items
|  | HEE | WEBSITE | FUNCTION |  | THRIVE ISSUE: MUST WAIT ON THEM. Fix the Start Course button. It should say Sign Up for Visitor, User not Logged In, or User not signed up for that course | 95% | 2022-05-12 | 2022-08-01 |  |  | TA should automatically make the change, but the Developers said that it is not working and they do not have a date for the correction. So I changed the text to Sign Up / Start Course
|  | HEE | WEBSITE | PAGES |  | Landing Page for Kickstarter book campaign | DEL | 2022-07-20 | 2022-08-08
|  | HEE | KEAP | EMAILS |  | Send Kickstarter email #1 | 100% | 2022-08-28 | 2022-09-01 |  | 2022-09-01 | Scheduled for 9/1/22
|  | HEE | KEAP | EMAILS |  | Send Kickstarter email #2 | 100% | 2022-08-28 | 2022-09-05 |  | 2022-09-03 | Scheduled for 9/5/22
|  | HEE | WEBSITE | FUNCTION |  | Create a Multi-pricing or Variable Product for EOY giving -- levels of donors and gifts. Price selected shows gifts they will get |  | 2022-05-15 | 2022-11-30 |  |  | Can do this in TC. Woo Simple product with Subscription like products now? Woo Variable product will work as long as it does not need to link to Apprentice Course
|  | HEE | WEBSITE | EMAILS |  | asdfasdf | 85% | 2022-08-31
Note on B1: 1) Task ID is only for easy identification in meetings, but most people use the Row Number. 2) Goal ID is the ID from the Goals tab that this Task is part of. 3) Person - who is responsible to complete the task. 4) Category - additional segmenting of the Task. 5) SubCat - further segmenting the Task if needed. 6) Priority of 1, 2, or 3. Leave blank if lower. 7) Item or Task Description - keep brief, prefer only one line. 8) % Complete is an estimate from Person, can include Tabled (TAB) or Deleted (DEL). 9) Inpute Date is the date the Task was input on the worksheet. 10) Due Date is often the next meeting. 11) Adj Date is new Due Date - DO NOT CHANGE THE DUE DATE COLUMN. 12) Comp Date is when the Task was completed. 13) Notes can be added in additional columns, but best to not print. 14) Do not delete tasks from the sheet even if completed (100%).
HELPFUL BEHAVIORS
Observational Listening – pictures what they are saying; paraphrases
Supports - encourages others to develop ideas; gives recognition
Probes - goes beyond the surface comments
Clarifies - asks for more information; clears up confusion
Offers Ideas - shares suggestions, solutions and proposals
Includes Others - asks quiet members for their opinion
Summarizes - pulls together ideas from a number of people
Manages Conflicts - listens to other's views; seeks solutions
HINDERING BEHAVIORS
Yeah But's, Blocks, Grandstands, Goes Off Topic, Dominates, Withdraws, Devil's Advocate, Criticizes, Personal Slurs
MEETING STRUCTURE / PROCESS
1. Next Meeting Date QUIT at
2. SUCCESSES & VALUES (Who you saw living our Values)
3. LIST Additional discussion items
4. REVIEW Assignments/Actions
5. DEFINE Discussion Items
6. SELECT Items for Discussion; Prioritize
7. DISCUSS Items
8. FOLLOW-UP Actions determined during meeting

## Discussion
Put a "Y" in the Select column for items to discuss. Filter by the "Y" or date for the discussion items needed for this meeting
It is better to not select the Notes for printing
Date | Input by | Select | Resp | Description | Topic/Issue | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments
2022-08-03 | HEE | y | Both | Review and update the status of Tasks on the worksheet. Add new tasks needed.
2022-08-03 | HEE |  | Joshua | SignUp Segue - can we use it?
2022-08-31 | HEE |  | Joshua | Course Enrollment sequences needed - Not started and Progress now - any more?
2022-09-14 | HEE |  | Joshua | Talk through Inactivity and Enrollment campaigns so we can identify what emails Tina needs to write
2022-09-14 | HEE |  | Joshua | Other campaigns needed for Nurture of Users?
2022-09-21 | HEE | y | Tina | Enrollment - first sequence 1) Welcome, 2) similar to welcome, 3) similar to welcome: 2 days between
2022-09-21 | HEE | y | Tina | Enrollment - In Progress sequence 1) Questions / statements about intitial course topics, 2) similar to welcome, 3) similar to welcome: 2 days between

## Goals
Goal ID Legend
C = Customer
W = Workforce (includes Leadership goals)
I = Information & Data (includes Financial, Strategic Planning)
O = Operations
KPI
Goal ID | Resp | Due Date | Adj Date | Description | THERE | HERE | As of Date | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments

## Goal Examples
Goal ID Legend
C = Customer
W = Workforce (includes Leadership goals)
I = Information & Data (includes Financial, Strategic Planning)
O = Operations
KPI
Goal ID | Resp | Due Date | Adj Date | Description | THERE | HERE | As of Date | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments | xx/xx/xx Comments
C1 | HEE | 2019-10-31 | 2019-09-30 | 3 new Customers: 2 Midland Basin, 1 Delaware Basin | 3,2,1 | 0,0,0 | 2019-03-10
C2 |  |  |  | Customer Satisfaction 4.5 | 4.5 | 3.7 | 2018-12-31
C3 |  |  |  | Create and update Opportunity List and Award Status by 5:00 PM Monday | List
C4 |  |  |  | Sign one customer to keep one water transfer frac crew busy ($300,000/month) | 1 $300k | 0
C5 |  |  |  | Execute contracts with Pioneer, Chevron, Crownquest, Hibernia and Endeavor for 2020 | 5 T1 | 1 T1
C6 |  |  |  | Weekly, accurate 90 day revenue forecast and job schedule each Monday by 5:00 PM | Every Wk Fcst | 10 of 17 Wks by 5P
C7 |  |  |  | Accurate Weekly Consumption Reports to Customers each Wednesday at 9:00 AM
I1 |  |  |  | 30% gross margin | 30% | 35%
I2 |  |  |  | $15MM per month | $15MM | $12MM
I3 |  |  |  | Budget to Actual variance <= 5%
I4 |  |  |  | Implement accurate Bidding and Budgeting process
W1 |  |  |  | Retention >= X% (xx/xx/xx)
W2 |  |  |  | Satisfaction >= X.X (xx/xx/xx)
W3 |  |  |  | Performance Scorecard >= 85% (xx/xx/19)
W4 |  |  |  | Hire 1 PM assist in budgeting and bidding process
W5 |  |  |  | Create Job and function checklist for top 5 processes
W6 |  |  |  | Create a performance scorecard for parks personnel
W7 |  |  |  | Create performance scorecard for superintendents/foremen
O1 |  |  |  | Overtime labor is <= 50% of Normal labor hours
O2 |  |  |  | X% Equipment Utilization owned and Y% Utilization rented
O3 |  |  |  | Implement Equipment Utilization Report - review Monday 10 AM
O4 |  |  |  | Accurate Job Costing/Tracking Report - review 10am Thursday

## Slogans
Select your Top10 with a "10" in the Top10 column, Top5 with "5", Top3 with "3", and #1
Purpose Slogan Ideas | Top10 | Top5 | Top3 | #1

## Core Values
Select your Top10 with a "10" in the Top10 column, Top5 with "5"
Core Value Ideas | Top10 | Top5

## Leader Behaviors
Leader Behavior Ideas | Top 10 | Top 5

## Brand Promise
Brand Promise Ideas | Top 10 | Top 5

## Goal Opp Rating
Label = The label you assigned to the idea, for example, "C6"
Goal Idea = A brief statement of the goal
Value = 1 is low, 10 is high
Success% = 0 to 100%
Effort = Estimated Management Effort is High (H), Medium (M), or Low (L)
|  | (1 to 10) | (0-100%) | (H-M-L)
Label | Goal Idea | Value | Success% | Effort

## Goal Impact-Effort
Label = The label you assigned to the idea, for example, "C6"
Goal Idea = A brief statement of the goal
Effort = Difficult "D" or Easy "E"
Impact = High "H" or Low "L"
EH = Easy to do and yields significant improvement (Implement immediately)
EL = Easy to do but yields slight improvement (Implement as resources allow)
DH = Difficult to do but yields significant improvement (Create a detailed plan)
DL = Difficult to do and yields slight improvement (Ignore)
|  | Effort | Impact
Label | Goal Idea | D or E | H or L